## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Display update succesfully to the screen |  | 1 | https://github.com/nekon0/SoWePray/issues/2 | Open | DuyPD | 2022-09-14 | 2022-09-18 | ite1 | Task | Update Admin profile
Data receive from Front end | Cant collect data from rating Form in book-details.jsp | 2 | https://github.com/nekon0/SoWePray/issues/10 | Open | DucTA | 2022-09-28 | 2022-10-02 | ite2 | Code | Book-details.jsp RatingController
Front end Comment interface | Create a textarea to show the previous comment | 3 | https://github.com/nekon0/SoWePray/issues/14 | Open | DucTA | 2022-09-30 | 2022-10-02 | ite2 | Interface | Book-details.jsp