## Backlog
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned
1 | Login | Common | Simple | Allow user to login in the system | 1
2 | Register | Common | Simple | Allow user to create an accout to have access to the web | 1
3 | Logout | Common | Simple | Allow user to logout in the system | 1
4 | Forget password | User | Medium | Forgot screen for user to enter his/her email in textbox. A random string will be set as user's new password after user click the link having reset token in the instruction email. | 1
5 | Home page | User | Medium | Show news intro and menu function | 1
6 | Change email | User | Medium | Show a pop-up for user to change their account's email
7 | Change Password | User | Simple | Show a pop-up for user to change their account's password | 1
8 | View profile | User | Simple | Show information of user | 1
9 | Update profile | User | Simple | Show a pop-up for user to change their account's properties | 1
10 | Library | Public | Simple | Allow user view a list of all books | 1
11 | View book description | Public | Simple | Allow user to view all the properties of each book | 1
12 | Pre-read | Public | Simple | Allow user to read the first chapter of the book
13 | View tables of contents | Public | Simple | Allow user to view book's catalogue
14 | Read a chapter | User | Simple | Allow user to read any chapter of the book
15 | Set reading interface | User | Medium | Allow user to set the reading interface as he/she like
16 | Filter | User | Medium | Allow user to find books that applied some details | 2
17 | Sort Engine | Common | Simple | List book by all kind of way
18 | Paging | Common | Simple | A system helps user to view a group of production at one
19 | Search book | Common | Simple | Allow user to search book by name | 2
20 | Comment | User | Simple | Allow user to write comment | 2
21 | Rate book | User | Simple | Allow user to rate the book they buy | 2
22 | Report a purchase | User | Medium | Customer can report their order if it has any trouble or cheating | 2
23 | Report book | User | Medium | Allow user to report the book that have issues | 2
24 | View all user's OW | User | Simple | Allow user to take a view on books of all users | 2
25 | Create a OW | User | Simple | Allow user to create his/her own work | 2
26 | Edit book's description | User | Simple | Allow user to edit description of their book | 2
27 | Write a chapter | User | Simple | Allow user to write his/her own book | 2
28 | Edit chapter's content | User | Simple | Allow user to edit the content of his/her index | 2
29 | Delete book | User | Simple | Allow user to delete his/her own book | 2
30 | Review book | User | Simple | Allow user to review the book (after reading) | 2
31 | Purchase a book | User | Simple | Allow user to purchase a book and add to their library | 2
32 | Purchase a chapter/volume | User | Simple | Allow user to purchase a paid chapter/volume to read | 2
33 | List book of this author | Common | Simple | Allow user/admin to see all the book of a specially author
34 | Payment | User | Simple | Allow user to choose method of depositing money into the wallet
35 | View purchase history | User | Simple | Allow user to see all the production that they bought in the past
36 | View bill | User | Simple | Allow user to access to the pop-up that shown the money user have to pay
37 | Share book | User | Medium | Allow user to share the link of the book to their friend through Facebook,...
38 | Ranking | User | Simple | Customer can promote if they pass their level of reputation when reading
39 | Login | Admin | Simple | Allow admin to login to the admin system | 1
40 | Logout | Admin | Simple | Allow admin to logout of the admin system | 1
41 | Forget password | Admin | Medium | Allow admin to receive new password when they forget the password\ | 1
42 | Admin panel | Admin | Simple | Home page for admin
43 | Change Password | Admin | Simple | Allow admin to change the password | 1
44 | View admin profile | Admin | Simple | Allow admin to view their profile | 1
45 | Edit admin profile | Admin | Simple | Allow admin to edit their profile | 1
46 | Add admin profile | Admin | Simple | Allow admin to add another admin profile | 2
47 | View list book | Admin | Simple | Allow admin to see all the book | 2
48 | Add book | Admin | Simple | Admin can add a new books with it's description | 2
49 | Edit book's description | Admin | Simple | Admin can update description of books | 2
50 | Edit book's index | Admin | Simple | Admin can update book's index to display | 2
51 | Edit book's content | Admin | Simple | Admin can update chapter's content | 2
52 | Dashboard | Admin | Medium | Overview about Page
53 | Turnover | Admin | Medium | Manage Outcome
54 | View list account | Admin | Simple | Admin can see information of customers | 2
55 | Manage user account | Admin | Medium | Disable/Up rank customer accounts | 2
56 | View purchase | Admin | Simple | Admin can view details , status of all orders
57 | Manage paid items | Admin | Medium | Admin can change status of all paid item
58 | Manage comment | Admin | Medium | If the comments contains inappropriate content, the admin delete it
59 | Manage Self Book | Admin | Simple | If the blog contains inappropriate content, the admin can send a warning to the blog owner or delete the blog
60 | Weekly sales | Common | Medium | Discount on promoted books and display every week
61 | Accumulated points | Common | Medium | System that control the points user can get or be abstracted
62 | View authors details | Common | Simple | Customer can see detail of their favourite author
63 | Add author details | Public | Simple | Allow user/admin to write and add information about the unknown author
64 | Edit author details | Public | Simple | Allow user/admin to edit information about the author
65 | Add to favor | User | Simple | Allow user to add the book to a libraby that stores all the book they like
66 | Delete from favor | User | Simple | Allow user to delete the book to a libraby that stores all the book they like
67 | Share list favor | User | Medium | Allow user to share the list of book or any book to others from the favor category

## Interation1
THE APPLICATION DEVELOPMENT PROJECT TOPIC ITERATION 1 PLANNING
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Screen Flow | # | Simple | 60 | HE161216 - Trịnh Anh Đức | Done
2 | Database scheme | # | Medium | 120 | HE161216 - Trịnh Anh Đức | Done
3 | Implementing Priorities | # | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done
4 | Login | Common | Simple | 60 | HE160308 - Phạm Đức Duy | Done
5 | Register | Common | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done
6 | Logout | Common | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
7 | Forget password | Common | Medium | 120 | HE163219 - Nguyễn Thành Vinh | Done
8 | Home page | Common | Medium | 120 | HE160135 - Nguyễn Thị Thanh Hiền | Done
9 | Change Password | Common | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done
10 | View profile | Common | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done
11 | Update profile | Common | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done
12 | View list book | Common | Simple | 60 | HE161216 - Trịnh Anh Đức | Done
13 | View book information | Common | Simple | 60 | HE161216 - Trịnh Anh Đức | Done
14 | View admin's profile | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | Done
15 | Edit Admin profile | Admin | Simple | 60 | HE160135 - Phạm Đức Duy | Done

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC ITERATION 2 PLANNING
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Comment | User | Simple | 60 | HE161216 - Trịnh Anh Đức | Doing
2 | Rate book | User | Simple | 60 | HE161216 - Trịnh Anh Đức | Doing
3 | Add to favor | User | Simple | 60 | HE161216 - Trịnh Anh Đức | Done
4 | Report book | User | Medium | 120 | HE161216 - Trịnh Anh Đức | Done
5 | Set reading interface | User | SImple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done
6 | Pre-read | Public | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done
7 | View tables of contents | Public | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done
8 | Read a chapter | User | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Pending
9 | Wallet | User | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | Done
10 | Purchase a book | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done
11 | View purchase history | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done
12 | Payment | User | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | Done
13 | Change Access Level | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | Done
14 | View list book | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
15 | Add book | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
16 | Edit book | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
17 | Disable book | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
18 | View table of contents | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
19 | Add Volume | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
20 | Edit Chapter | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
21 | Delete Volume | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
22 | Add Chapter | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
23 | Delete Volume | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
24 | Delete Chapter | Admin/Staff | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done
25 | View list account | Admin/Staff | Simple | 60 | HE160308 - Phạm Đức Duy | Done
26 | Manage user account | Admin/Staff | Medium | 120 | HE160308 - Phạm Đức Duy | Done
27 | Change Email | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done