## Cover Page
OLS Qualification
TEST STRATEGY
Purpose
To define test strategy and plan how and what we will qualify 2.8.4 base on defined scope
Project Effort
Contents
| Test scopes | <Mandatory> Defines the test items; features are tested, not to tested; acceptant criterias
| Test strategies | <Mandatory> Defines strategies; priorities; test method/technique/type/level will be used
| Environment & Resource | <Optional> Defines all needed resources (human, device, PC, platforms…)
| Test risks | <Mandatory> Defines test assumption/risk/issue and corresponding actions
| Test plan and deliveries | <Optional> Defines the plan and deliveries
| Communication | <Optional> Communication channels and tools supports
Estimation Cost
TestedRemainedTestCases
TaskDetail
Base of Estimation
Record of change
RECORD OF CHANGES
| Version | Date | Change details
| 1 | 2012-12-06
| Creator: | Hanh | Create Date: 6 Dec 2012
| Reviewer: | Hanoi OLS team | Review Date: 10 Dec 2012
| Approver: | Akriche.Akka Philippe | Approve Date:

## Test scopes
TEST SCOPE:
The scope of testing should cover following items:
A. Test items
<Test items is the items is going to be tested. It could includes the functional or non-functional request.
It could be the use case, functionalities, testing request from customer…>
A1. Features are to be tested:
Below functions need to be tested following 2.8.4 release note:
| 1 | OLS installation and deployment
| 2 | Qualify all CRs/PRs of R2.8.4 as Release Note;
| 3 | Regresstion test on basic cases of all areas: Opco Web, BOI - NISL, Configuration management, Feature Management
Rate download, Econfirmation, Software download
MOD, Slogan and Diagnostics, Statistics
| 4 | Cover Alpha1, DELTA, Omega, DS 90, IJ on either US or EU
A2. Features are not to be tested:
<List out all features are not to be tested to CLEAR the boundary of testing and DO not make the confusing of scope>
| 1 | No performance test
B. Acceptant criterias of testing
< Acceptant criterias are the agreement with customer, develop team, stakeholders when testing is enough and how sufficient of testing
It could be the statement of word but should quantitatize by metrics such as following:
- Test Coverage (%): counted by the tested functions or features/ total of functions or features.
- Successful Test Coverage (%)
- % Executed Test Case
- % Defect found by test.
- Leakage…>
No big problem on deployment and main functions in the production (need Philippe confirm this)
Need Akriche.Akka Philippe put information here as your expection as acceptance OLS qualification

## Test strategy
TEST STRATEGY
<Defines strategies; priorities; test method/technique/type/level will be used>
Test approaches include following items:
A. TEST STRATEGY:
| 1 | Focus on list of 2.8.4 PRs first (finish on 15-Dec-12)
| 2 | Regression test on Basic testing for all areas on IS (Alpha1, Omega, Delta), DS and IJ, focus on areas: Statistics, OpcoWeb
| 3 | All critical problems or CRs/PRs that are "reworked" will be reported before 15-Dec-12.
And if there will be any db-patches or OLS patches, re-testing will be done after that.
B. TEST METHOD:
All testing activiities is manual test
C. TEST CYCLES (test level/phase and the corresponding test type and test technique)
Main activity
# | Activity |  | Scope of Test Level | Estimate Effort (hours)
1 | Deployment qualification |  | Following installation guide. No error as guideline mention to. | 7
2 | Study release note & CR/PR, make QnA |  | Make clear biz understanding | 30
4 | Prepare devices for testing |  | For qualification (QLF) activity | 15
5 | Qualify PRs/Requests |  | Cover 100% 1 round PR/CRs and the impact of fixing those | 70
6 | Regresstion test |  | Test on main functions | 182
7 | Planning & Reporting |  | For QLF activity | 30
8 | Cross review within the team |  | Focus review on PRs/CRs need to be qualified and new found PRs | 10
9 | Final inspection to check testing quality from other team |  | Review test result and random test CR/PR QLF by other team | 10
10 | Management |  | For QLF activity | 50
11 | Buffer for risk in Devices and some other issues |  | For QLF activity | 10
|  |  | Total | 414
Note on G18: Consider as the complete criteria

## Test plan and deliverable
TEST PLAN and DELIVERABLES
<Decribe the planning and deliverables>
1. Week 1: 4-7/Dec (4 days):
- Back up database (both US and EU) before install and deploy 2.8.4
- Understanding requirement, make questions and get answers
- Reproduce problems
- Deploy 2.8.4 on both US and EU;
- Start qualifying CRs/PRs
2. Week 2: 10-15/Dec (6 days):
- Continue qualifying CRs/PRs
- Start regression test on basic testing for all areas on IS (Alpha1, Delta, Omega), DS 90 and IJ
- Qualifying db-patch: v2.8.3-db42 v3; v2.8.3-db62 v2; v2.8.3-db35; v2.8.3-db36 v3 on 2 days(10/11-Dec)
- Any new critical PRs or PRs/CRs that are "REWORKED" will be reported daily.
- Weekly report will be sent at the end of the week
3. Week 3: 17-21/Dec (5 days):
- Continue regression test on basic testing for all areas on IS (Alpha1, Delta, Omega), DS and IJ
- Be sure that all critical PRs of 2.8.4 will be found and will be reported before 19-Dec
- Weekly report will be sent at the end of the week
4. Week 4: 24-28/Dec (5 days):
- Continue to basic testing (if there will be a new version of 2.8.4)
'- If there is a new patch for 2.8.4 (for example 2.8.4_v2) before 24-Dec-2012, it will be continued to qualify (PRs/CRs – regression test) and still have GO on 03-Jan-2013
5. Week 5: 2-3/Jan/2013 (2 days):
- Continue to basic testing (if there will be a new version of 2.8.4)
- Do final inspection and send final report on 03-Jan-2013
- If there is a new patch for 2.8.4 (for example 2.8.4_v2, v3...) in this week, the GO will be postponed

## Test risks
TEST ISSUEs/RISKs
<Defines test assumption/risk/issue and corresponding actions>
A. TEST ASSUMPTIONs
<Describe the assumption of this strategy>
| 1 | if there is any big issue that impact to testing (example server deployment issue, network issue,..),
it will be discussed with Bagneux team to extent the time for qualification
B. TEST ISSUEs
<Describe the test issues and the action to solve>
| # | Issue Name | Issue Description | Action to solve | Notes
C. TEST RISKs
<Describe the test risks and the action to mitigate and define the contingency>
| # | Risk Name | Risk Description | Contingency Action | Mitigation Actions
| 1 | Some device releases must be qualified on the same time to qualify 2.8.4. | - During the period of qualifying OLS R2.8.4, there are three received qualification requests for device release: Alpha1 NO, Alpha1 FI, OmegaII US |  | Integrate of testing OLS R2.8.4 and device release: Alpha1 NO, Alpha1 FI, OmegaII US

## Communication
TEST COMMUNICATION
<Communication channels and tools supports>
A. COMMUNICATION CHANNELs:
| # | Communication Items | Type | Frequency | Participants | Scope of Communication
| 1 | Daily meeting | Communicator | Everyday | Lan, Giang and Philippe | Progress of testing Quality of testing and quality of application
| 2 | Problem Report | Windchill | Live | Hanoi QLF | Report any problem finding
| 3 | Project Dashboard | Dashboard | Live | Persons have authorization to access (Hanoi QLF, Bagneux team)
| 4 | Weekly Meeting | PhoneLine/ Communicator | Weekly | Lan and Anthony | Discuss about progress and issue if have
B. TOOL SUPPORT COMMUNICATION
| # | Tools | Participants | Frequency | Scope
| 1 | Dashboard | PJ team | Live | Present Project status
| 2 | Windchill | PJ team | Live | Problem Report
| 3 | Redmine | PJ team | Live | Problem Report

## Detail tasks
User story | Tasks name | Task description | Assignment | Time (hours)
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | ChinhNTM | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | ChinhNTM | 4
R2.8.4_QualifyPRs | PR00006586 | Optimization - Grouping of Statistics + Data collection profile must be modified in order to be able to exclude a machine from regroupment | ChinhNTM | 5
R2.8.4_QualifyPRs | PR00004268 | the money of the report activity in OLS is not good | ChinhNTM | 6
R2.8.4_QualifyPRs | PR00005248 | AR_10503-Opco IE: MBO - IS Stat contract - Impossible to modify advanced contract with 13 months | ChinhNTM | 4
R2.8.4_QualifyPRs | PR00006501 | CRM Stats - Ability to change the CRM Level per Machine | ChinhNTM | 5
R2.8.4_Regression test | STATISTICS - Regression test | STATISTICS - Regression test | ChinhNTM | 16
R2.8.4_Regression test | STATISTICS - LDLD | STATISTICS - LDLD | ChinhNTM | 14
R2.8.4_Review/FI | Support FI | Support FI | ChinhNTM | 2
R2.8.4_Prepare devices | Prepare devices | Prepare devices | ThomLT | 8
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | ThomLT | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | ThomLT | 4
R2.8.4_QualifyPRs | PR00007630 | OSYS RU osiris: Question mark sign "?" is visible in detailed usage statistics | ThomLT | 1
R2.8.4_QualifyPRs | PR00003486 | QLF R2.8.2.1_FR_Cusweb :Some pages of Customer Web and export files are not consistant about : department status ,Operator status and currency | ThomLT | 2
R2.8.4_QualifyPRs | PR00004937 | Erroneous characters displayed in Customer Web | ThomLT | 1
R2.8.4_QualifyPRs | PR00005915 | Opco CA - Difference between Customer Web and MyEquipent | ThomLT | 1
R2.8.4_QualifyPRs | PR00003297 | AR_09783-Opco US: WWeb - Caption correction on customer web We need to change “Signature available” to “Signature Available” in customer web (Home > Tracking). | ThomLT | 1
R2.8.4_QualifyPRs | PR00007954 | AR_10981-OLS_No Econfirmation manifest reports after 10/19/2012 | ThomLT | 1.5
R2.8.4_Regression test | ECONFIRMATION Regression test | ECONFIRMATION Regression test | ThomLT | 14
R2.8.4_Regression test | CusWeb-Regression test | CusWeb-Regression test | ThomLT | 8
R2.8.4_Review/FI | Support FI | Support FI | ThomLT | 2
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | HoaHTK | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | HoaHTK | 4
R2.8.4_Prepare devices | R2.8.4_Prepare devices | R2.8.4_Prepare devices | HoaHTK | 10
R2.8.4_Regression test | RATE DOWNLOAD - Request Handler | RATE DOWNLOAD - Request Handler | HoaHTK | 42
R2.8.4_QualifyPRs | PR00004696 | QLF_R2.8.3_UK+GER_Rate download: Incorrect email sent when manual trigger RPC with In Progress and Active Rate | HoaHTK | 7
R2.8.4_Review/FI | Support FI | Support FI | HoaHTK | 2
R2.8.4_QualifyPRs | Anomalie #4283 | Linked to Anomalie #3726 already corrected | HanhTH | 4
R2.8.4_Regression test | FM - Regression test | FM - Regression test | HanhTH | 21
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | HanhTH | 8
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | HanhTH | 4
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | ThuQTC | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | ThuQTC | 4
R2.8.4_QualifyPRs | PR00004733 | QLF_EU_R2.8.3_CM_KEOPS: serverPhoneNumber was modified from 147 to “null” on device after the call download new suffix | ThuQTC | 2
R2.8.4_QualifyPRs | PR00006500 | Postal Core phone number must be added in Network Migration | ThuQTC | 3
R2.8.4_QualifyPRs | PR00005292 | AR_10516-Opco FR - OMEGA-FT-OLS-Ink Information missing for print head | ThuQTC | 1
R2.8.4_Regression test | CM - Regression test | CM - Regression test | ThuQTC | 46
R2.8.4_Regression test | Ink-Regression test | Ink-Regression test | ThuQTC | 8
R2.8.4_Review/FI | Support FI | Support FI | ThuQTC | 2
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | TungNX | 1.5
R2.8.4_Server Deployment | Server Deployment | Server Deployment | TungNX | 7
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | TungNX | 4
R2.8.4_QualifyPRs | Évolution #5529 | Add the missing column in order we can see all columns of the table RELEASE_HISTORY | TungNX | 2
R2.8.4_QualifyPRs | PR00004232 | QLFR2.8.2.4_OpCoLUX_Cannot add Rate contract by MBO including ATTRIBUTE "transactionNb" | TungNX | 1.5
R2.8.4_QualifyPRs | PR00004731 | QLF_2.8.3_MBO&NISL:Could not add/update RateDownload contract when Number of Deliveries has value | TungNX | 1.5
R2.8.4_QualifyPRs | PR00007312 | 2 new features for Omega : SLOGAN_DOWNLOAD_FROM_USBKEY et TRACKING_BARCODE_REPORT_AUTOMATION | TungNX | 10
R2.8.4_Regression test | BOI - Regression test | BOI - Regression test | TungNX | 10
R2.8.4_Review/FI | Support FI | Support FI | TungNX | 2
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | TrangBT | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | TrangBT | 4
R2.8.4_QualifyPRs | PR00003738 | QLF_Allcount_2.8.2.2_Slogan:After Download Default Slogan and Customize Slogan, Friendly Name is displayed same name File Name | TrangBT | 4
R2.8.4_QualifyPRs | PR00004009 | QLF_US_2.8.2.3_MOD: Message hasn't displayed when adding Communication Message with status On selected systems | TrangBT | 4
R2.8.4_Regression test | MOD, Slogan, Diagnostic - Regression test | MOD, Slogan, Diagnostic - Regression test | NgaTTT2 | 14
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | MyDT | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | MyDT | 4
R2.8.4_QualifyPRs | PR00004003 | QLF_Allcount_2.8.2.3_OpCoWeb: Action "Automatic Notifications " performs incorrectly | MyDT | 1.5
R2.8.4_QualifyPRs | PR00004719 | QLF_R2.8.3_Opco web_Lux : Display "HTTP Status 500 - " page when focus on field "Department List Download Description" then press "Enter" key on keyboard. | MyDT | 1
R2.8.4_QualifyPRs | PR00004738 | QLF_Allcount_2.8.3_OpCo Web: The deletion of the role can be done if there are users having the role deleted as a unique role | MyDT | 1.5
R2.8.4_QualifyPRs | PR00004756 | QLF_Allcount_2.8.3_OpCo Web: Lack of Meter Die information from software report of DS(all status) and MS (WITHDRAW status) in download tracking | MyDT | 2
R2.8.4_QualifyPRs | Anomalie #5743 | Correct the screen in order that it must be compliant with : 1st : Opco_id is determined; Locale is determined 2nd: Opco_id is determined; Locale is null (all locale) 3rd: Opco_id is null (all opco); Locale is determined 4th: Opco_id is null (all opco); Locale is null (all opco) | MyDT | 14
R2.8.4_QualifyPRs | PR00002261 | unable to create user message appears RuntimeException | MyDT | 1
R2.8.4_QualifyPRs | PR00002419 | Opco FR: Fusion Monitoring - View Franking - Impossible to view a full month | MyDT | 1
R2.8.4_QualifyPRs | Évolution #5674 | Remove Satas from Home page | MyDT | 0.5
R2.8.4_QualifyPRs | PR00005046 | AR_10061-MAS CONNECT - Fusion Monitoring tool - Franking date at midnight for all machine | MyDT | 3
R2.8.4_Regression test | OpCoWeb-Regression test | OpCoWeb-Regression test | MyDT | 21
R2.8.4_Review/FI | Support FI | Support FI | MyDT | 2
R2.8.4_Study requirement/QnA_EstimateTime | Estimate time | Estimate time | NgaTTT2 | 1.5
R2.8.4_Others | R2.8.4_Others | R2.8.4_Others | NgaTTT2 | 4
R2.8.4_QualifyPRs | Anomalie #4034 | Code review: delete/inactivate soft config pack | NgaTTT2 | 7
R2.8.4_QualifyPRs | Anomalie #4284 | Calculating problem for software link (software installed on system) to systems | NgaTTT2 | 6
R2.8.4_QualifyPRs | OSIRIS_CR_3845/PR00004703 | QLF_R2.8.3_CR_3845: "Check" button is not displayed on "Software Package Add" and "Software Package Edit" screens Tested on UK, Neopost, Hasler: Check button is only displayed at Software Package Details screen and it is not displayed on Software Package Edit and Software Package Add screens as DFS | NgaTTT2 | 2
R2.8.4_QualifyPRs | PR00007857 | QLF R2.8.3.4_DS90_NL_BCR2D: Some setting parameters displays on OpcoWeb differently from on device | NgaTTT2 | 6
R2.8.4_Regression test | SWDL - Regression Test | SWDL - Regression Test | NgaTTT2 | 42
R2.8.4_Regression test | DS-Regression test | DS-Regression test | ChinhNTM | 14
R2.8.4_Review/FI | Support FI | Support FI | ChinhNTM | 2
R2.8.4_Review/FI | Support FI | Support FI | NgaTTT2 | 2
User Story | Sum of Time (hours)
R2.8.4_Review/FI | 16
R2.8.4_Others | 36
R2.8.4_Prepare devices | 18
R2.8.4_QualifyPRs | 114
R2.8.4_Regression test | 270
R2.8.4_Server Deployment | 7
R2.8.4_Study requirement/QnA_EstimateTime | 20
Grand Total | 481