## Backlog
# | Function/Screen | Feature | Level* | Function/Screen Details | Incharge | Status | Planned | Actual | Update | Note
1 | Login | Common | Simple | Allow user to login in the system | Duy | Done | 1 | 1 | none
2 | Register | Common | Simple | Allow user to create an accout to have access to the web | Hiền | Done | 1 | 1 | none
3 | Logout | Common | Simple | Allow user to logout in the system | Vinh | Done | 1 | 1 | none
4 | Forget password | User | Medium | Forgot screen for user to enter his/her email in textbox. A random string will be set as user's new password after user click the link in the instruction email. | Vinh | Done | 1 | 1 | none
5 | Home page | User | Medium | Show news intro and menu function | Hiền | Done | 1 | 1 | none
6 | Change email | User | Medium | Show a pop-up for user to change their account's email | Ánh | Done | 2 | 2 | none |  | `
7 | Change Password | User | Simple | Show a pop-up for user to change their account's password | Ánh | Done | 1 | 1 | none
8 | View profile | User | Simple | Show information of user | Ánh | Done | 1 | 1 | none
9 | Update profile | User | Simple | Show a pop-up for user to change their account's properties | Ánh | Done | 1 | 1 | none
10 | Library | Public | Simple | Allow user view a list of all books | Đức | Done | 1 | 1 | none
11 | View book description | Public | Simple | Allow user to view all the properties of each book | Đức | Done | 1 | 1 | none
12 | Pre-read | Public | Simple | Allow user to read the first chapter of the book | Hiền | Done | 2 | 2 | none
13 | View tables of contents | Public | Simple | Allow user to view book's catalogue | Hiền | Done | 2 | 2 | none
14 | Set reading interface | User | Medium | Allow user to set the reading interface as he/she like | Hiền | Done | 2 | 2 | none
15 | Filter | User | Medium | Allow user to find books that applied some details | Đức | Done | 3 | 3 | none
16 | Sort Engine | Common | Simple | List book by all kind of way | Đức | Done | 3 | 3 | none
17 | Paging | Common | Simple | A system helps user to view a group of production at one | Đức | Done | 3 | 3 | none
18 | Search book | Common | Simple | Allow user to search book by name | Đức | Done | 3 | 3 | none
19 | Comment | User | Simple | Allow user to write comment | Đức | Done | 2 | 2 | none
20 | Rate book | User | Simple | Allow user to rate the book they buy | Đức | Done | 2 | 2 | none
21 | Report a transaction | User | Medium | Customer can report their order if it has any trouble or cheating | Đức | Done | 4 | 4 | none
22 | Report book | User | Medium | Allow user to report the book that have issues | Đức | Done | 2 | 2 | none
23 | View all user's novel | User | Simple | Allow user to take a view on books of all users | Vinh | Done | 3 | 3 | none
24 | Create a novel | User | Simple | Allow user to create his/her own work | Vinh | Done | 3 | 3 | none
25 | Edit novel's information | User | Simple | Allow user to edit description of their novel | Vinh | Done | 3 | 3 | none
26 | Add a chapter | User | Simple | Allow user to write chapter of her novel | Vinh | Done | 3 | 3 | none
27 | Edit chapter | User | Simple | Allow user to edit the content of his/her chapter | Vinh | Done | 3 | 3 | none
28 | Purchase a book | User | Simple | Allow user to purchase a book and add to their library | Ánh | Done | 2 | 2 | none
29 | Purchase a chapter | User | Simple | Allow user to purchase a paid chapter of user's book | Ánh | Done | 4 | 4 | none
30 | List book of this author | Common | Simple | Allow user/admin to see all the book of a specially author | Hiền | Done | 3 | 3 | none
31 | Payment | User | Simple | Allow user to see balance in his/her wallet and send withdraw or deposit request to admin | Ánh | Done | 2 | 2 | none
32 | View purchase history | User | Simple | Allow user to see all the production that they bought in the past | Ánh | Done | 2 | 2 | none
33 | Wallet | User | Simple |  | Ánh | Done | 2 | 2 | none
34 | BookShelf | User | Simple | Store all the book that user has bought, added to favor and written | Ánh | Done | 3 | 3 | none
35 | View security status | User | Simple | Allow user to see the status of password and email. They can change these information in this screen | Ánh | Done | 1 | 1 | none
36 | Add to favorite | User | Simple | Allow user to add books into their favorite list | Đức | Done | 2 | 2 | none
37 | Delete from favorite | User | Simple | Allow user to remove books from their favorite list | Đức | Done | 3 | 3 | none
38 | Admin panel | Admin | Simple | Home page for admin | Duy | Done | 3 | 3 | none
39 | Change Password | Admin | Simple | Allow admin to change the password | Ánh | Done | 1 | 1 | none
40 | View admin profile | Admin | Simple | Allow admin to view their profile | Duy | Done | 1 | 1 | none
41 | Edit admin profile | Admin | Simple | Allow admin to edit their profile | Duy | Done | 1 | 1 | none
42 | Disable book | Admin | Simple | Allow admin to disable books and make them disappeared from library | Vinh | Done | 2 | 2 | none
43 | View all book | Admin | Simple | Allow admin to see all the book | Vinh | Done | 2 | 2 | none
44 | Add book | Admin | Simple | Admin can add a new books with it's description | Vinh | Done | 2 | 2 | none
45 | Edit book | Admin | Simple | Admin can update books | Vinh | Done | 2 | 2 | none
46 | Edit Table of content | Admin | Simple | Admin can update book's table of content | Vinh | Done | 2 | 2 | none
47 | Dashboard | Admin | Medium | Overview about Page | Duy | Done | 3 | 3 | none
48 | View list account | Admin | Simple | Admin can see information of customers | Duy | Done | 2 | 2 | none
49 | Manage user account | Admin | Medium | Disable/Up rank customer accounts | Duy | Done | 2 | 2 | none
50 | Report a comment | User | Simple | Allow user to report comment that violate the community rules | Hiền | Done | 4 | 4 | none
51 | Ban Comment | Admin | Simple | If the comments contains inappropriate content, the admin can ban it | Hiền | Done | 4 | 4 | none
52 | Manage Novel | Admin | Simple | If the novel contains inappropriate content, the admin can ban the novel | Vinh | Done | 4 | 4 | none
53 | Ticket | User | Simple |  | Duy | Done | 4 | 4 | none
54 | View author details | Admin | Simple | Allow user/admin to write and add information about the unknown author | Duy | Done | 3 | 3 | none
55 | Edit author details | Admin | Simple | Allow user/admin to edit information about the author | Duy | Done | 3 | 3 | none
56 | View reports | Admin | Simple |  | Vinh | Done | 4 | 4 | none
57 | Solve reports | Admin | Simple |  | Vinh | Done | 4 | 4 | none
58 | Manage Category | Admin | Medium | Allow admin to see, add, update or delete category | Ánh | Done | 3 | 3 | none
59 | Manage transaction | Admin | Simple | Allow admin to see list of all user's transaction, choose to accept or reject pending withdraw/deposit request | Ánh | Done | 4 | 4 | none
60 | Delete Novel | User | Simple | Allow user to delete his/her own novel | Vinh | Done | 3 | 3 | none
61 | Wallet | User | Simple |  | Ánh | Done | 2 | 2 | none
62 | Add/Delete/Edit Volum | Admin | Simple |  | Vinh | Done | 2 | 2 | none
63 | Delete Chapter | Admin | Simple |  | Vinh | Done | 2 | 2 | none
64 | Edit Novel Chapter | User | Simple |  | Hiền | Done | 3 | 3 | none
65 | Notification | Common | Simple |  | Duy | Done | 4 | 4 | none
66 | Author Profile | User | Simple | Allow user to see the default information about the author they want to see | Hiền | Done | 4 | 4 | none

## Interation1
THE APPLICATION DEVELOPMENT PROJECT TOPIC ITERATION 1 PLANNING
# | Function/Screen | Feature | Level* | LOC | In Charge | SRS | SDS | Status | Notes
1 | Login | Common | Simple | 60 | HE160308 - Phạm Đức Duy | II.2.1 | II.2.1 | Done
2 | User Register | Common | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | II.2.2 | II.2.2 | Done
3 | Logout | Common | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.2.4 | II.2.4 | Done
4 | Forget password | Common | Medium | 120 | HE163219 - Nguyễn Thành Vinh | II.2.3 | II.2.3 | Done
5 | Homepage | Public | Medium | 120 | HE160135 - Nguyễn Thị Thanh Hiền | II.1 | II.1 | Done
6 | Change password | Common | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.2.5 | II.2.5 | Done
7 | View profile | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.3.1 | II.3.3 | Done
8 | Update profile | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.3.2 | II.3.4 | Done
9 | Library | Public | Simple | 60 | HE161216 - Trịnh Anh Đức | II.5.8 | II.5.12 | Done
10 | View book's detail | Public | Simple | 60 | HE161216 - Trịnh Anh Đức | II.5.3 | II.5.5 | Done
11 | View admin's profile | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | II.3.3 | II.3.1 | Done
12 | Edit Admin profile | Admin | Simple | 60 | HE160135 - Phạm Đức Duy | II.3.4 | II.3.2 | Done
13 | Viewsecurity status | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.3.5 | II.3.5 | Done

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC ITERATION 2 PLANNING
# | Function/Screen | Feature | Level* | LOC | In Charge | SRS | SDS | Status | Notes
1 | Comment | User | Simple | 60 | HE161216 - Trịnh Anh Đức | II.10.1 | II.13.1 | Done
2 | Rate book | User | Simple | 60 | HE161216 - Trịnh Anh Đức | II.5.7 | II.5.10 | Done
3 | Add to favor | User | Simple | 60 | HE161216 - Trịnh Anh Đức | II.9 | II.12.1 | Done
4 | Report book | User | Simple | 60 | HE161216 - Trịnh Anh Đức | II.5.6 | II.5.12 | Done
5 | Book Reading Interface | User | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | II.5.4 | II.5.8 | Deferred
6 | Book Prereading | Public | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | II.5.4 | II.5.9 | Done
7 | View tables of contents | Public | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | II.5.5 | II.5.7 | Done
8 | Wallet | User | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | II.12.3 | II.15.1 | Done
9 | Purchase a book | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.12.1 | II.15.7 | Done
10 | View purchase history | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.12.3a | II.15.1 | Done
11 | Payment | User | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | II.12.3 | II.15.1 | Done
12 | Change Access Level | Admin | Simple | 60 | HE160308 - Phạm Đức Duy |  |  | Done
13 | View all Books | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.1 | II.5.4 | Done
14 | Add book | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.1 | II.5.1 | Done
15 | Edit book | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.1 | II.5.2 | Done
16 | Disable book | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.1 | II.5.3 | Done
17 | View table of contents | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | II.5.6 | Done
18 | Add Volume | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | II.6.1 | Done
19 | Edit Volume | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | ii.6.2 | Done
20 | Delete Volume | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | II.6.3 | Done
21 | Add Chapter | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | II.7.1 | Done
22 | Edit Chapter | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | II.7.2 | Done
23 | Delete Chapter | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | II.5.5 | II.7.3 | Done
24 | View list account | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | II.4 | II.4.1 | Done
25 | Manage user account | Admin | Medium | 120 | HE160308 - Phạm Đức Duy | II.4 | II.4.2 | Done
26 | Change Email | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | II.2.6 | II.2.6 | Done

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC ITERATION 3 PLANNING
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | SRS | SDS | Notes
1 | [Update] Library | User | Medium | 120 | HE161216 - Trịnh Anh Đức | Done | II.5.8 | II.5.12
2 | Delete from favorite | User | Simple | 60 | HE161216 - Trịnh Anh Đức | Done | II.9 | II.12.2
3 | Create a novel | User | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.6.1.b | II.8.1
4 | Edit novel's information | User | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.6.1.c | II.8.2
5 | Delete novel | User | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.6.1.c | II.8.3
6 | View all user's novel | User | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.6.1.a | II.10.3
7 | Add Novel Chapter | User | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.6.2.a | II.9.1
8 | Edit Novel Chapter | User | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.6.2.b | II.9.2
9 | Delete Novel Chapter | User | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.6.2.c | II.9.3
10 | List book of this author | Common | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.5.9 | II.5.13
11 | Purchase a chapter | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Deferred |  |  | Wait for read OW function
12 | Share book | User | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | Deferred |  |  | Cannot share localhost url
13 | Manage Category | Admin | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | Done | II.8 | II.11
14 | Admin panel | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | Done | II.16 | II.18
15 | View authors | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | Done | II.7 | II.10.1
16 | Edit author details | Admin | Simple | 60 | HE160308 - Phạm Đức Duy | Done | II.7 | II.10.2
17 | Bookshelf | User | Medium | 120 | HE163997 - Khuất Thị Minh Ánh | Done | II.14 | II.16

## Iteration 4
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | SRS | SDS | Notes
1 | Purchase a novel's chapter | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done | II.12.1 | II.47
2 | [Update] View payment status | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done | II.12.3a | II.25, II.26, II.27
3 | [Update] Withdraw | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done | II.12.3b | II.25, II.26, II.27
4 | [Update] Deposit | User | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done | II.12.3c | II.25, II.26, II.27
5 | View reports | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.11 | II.42
6 | Solve report | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.11 | II.42
7 | Ticket | User | Simple | 60 | HE160308 - Phạm Đức Duy | Done | II.15 | II.48
8 | Manage transactions | Admin | Simple | 60 | HE163997 - Khuất Thị Minh Ánh | Done | II.12.3d | II.46
9 | Ban Comment | Admin | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.10.3 | II.14.5
10 | Report a comment | User | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.10.2 | II.14.6
11 | Notification | Common | Simple | 60 | HE160308 - Phạm Đức Duy | Done | II.17 | II.49
12 | Edit Comment | User | Medium | 60 | HE161216 - Trịnh Anh Đức | Done | II.12.3 | II.50
13 | Report Transactions | User | Simple | 60 | HE161216 - Trịnh Anh Đức | Done | II.12.4 | II.15.8
14 | View author's information | Common | Simple | 60 | HE160135 - Nguyễn Thị Thanh Hiền | Done | II.13 | II.13
15 | Delete Comment | User | Medium | 60 | HE161216 - Trịnh Anh Đức | Done | II.12.4 | II.50
16 | Reply Comment | User | Medium | 60 | HE161216 - Trịnh Anh Đức | Done | II.12.2 | II.50
17 | Manage Novel | Admin | Simple | 60 | HE163219 - Nguyễn Thành Vinh | Done | II.5.1 | II.5.4