## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Display update succesfully to the screen |  | 1 | https://github.com/nekon0/SoWePray/issues/2 | Closed | DuyPD | 2022-09-14 | 2022-09-18 | ite1 | Task | Update Admin profile
Data receive from Front end | Cant collect data from rating Form in book-details.jsp | 2 | https://github.com/nekon0/SoWePray/issues/10 | Closed | DucTA | 2022-09-28 | 2022-10-02 | ite2 | Code | Book-details.jsp RatingController
Front end Comment interface | Create a textarea to show the previous comment | 3 | https://github.com/nekon0/SoWePray/issues/14 | Closed | DucTA | 2022-09-30 | 2022-10-02 | ite2 | Interface | Book-details.jsp
Load Data for Book's Author | Book's author is not show author name but something other | 4 | https://github.com/nekon0/SoWePray/issues/18 | Closed | AnhKTM | 2022-10-07 | 2022-10-16 | iter3 | Code | Book.Author
Backend mistake | Book "Gone Girl" always be opened when choose any book | 5 | https://github.com/nekon0/SoWePray/issues/20 | Closed | AnhKTM | 2022-10-08 | 2022-10-16 | iter3 | Code | GetBookID() in BookDetailController
Load Data from database for search | Show all book by category is not working | 6 | https://github.com/nekon0/SoWePray/issues/22 | Closed | AnhKTM | 2022-10-07 | 2022-10-16 | iter3 | Code | BookDAO
Interface changer not working | Can not use the change text style in Preread | 7 | https://github.com/nekon0/SoWePray/issues/21 | Closed | AnhKTM | 2022-10-07 | 2022-10-24 | iter3 | Code
Book sale problem | Book is sale with price $5 but still sold with origin price | 8 | https://github.com/nekon0/SoWePray/issues/19 | Closed | AnhKTM | 2022-10-07 | 2022-10-24 | iter3 | Code
Menu bar not working | Cannot open menu bar on Book Detail screen | 25 | https://github.com/nekon0/SoWePray/issues/25 | Closed | AnhKTM | 2022-11-02 | 2022-11-07 | iter4 | Interface | Book-details.jsp
Rate book no star | Click "Rate" button without select rate lead to error 500 | 26 | https://github.com/nekon0/SoWePray/issues/26 | Closed | AnhKTM | 2022-11-02 | 2022-11-13 | iter5 | Code | RatingController.java
Chapters issue | Arrange chapter button on TOC screen lead to 404 error | 27 | https://github.com/nekon0/SoWePray/issues/27 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Function | chapter-details.jsp
Free novel issue | Cannot read free novel | 28 | https://github.com/nekon0/SoWePray/issues/28 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | BookDetailController, Book Detail Screen
Function issue | Cannot open novel detail when didn't login | 30 | https://github.com/nekon0/SoWePray/issues/30 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | BookDetailController, book-detail.jsp
Content issue | Table of content show not done chapter | 31 | https://github.com/nekon0/SoWePray/issues/31 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Interface | book-detail.jsp
View not increase | Number of view not increase | 32 | https://github.com/nekon0/SoWePray/issues/32 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | BookReadingController, book-reading.jsp
Comment issue | Cannot edit comment or reply other reply in own comment | 34 | https://github.com/nekon0/SoWePray/issues/34 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | CommentController, ReplyController
Button issue | Home button in book reading screen not working | 35 | https://github.com/nekon0/SoWePray/issues/35 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Interface | Read Screen
Admin issue | Admin's user management not show all users | 36 | https://github.com/nekon0/SoWePray/issues/36 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | UserManager
Author manage issue | Clearing author's name is so easy | 37 | https://github.com/nekon0/SoWePray/issues/37 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | AuthorManage
Authorization issue | Admin cannot read or buy any book | 38 | https://github.com/nekon0/SoWePray/issues/38 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Code | BookDetail Screen, BookReadingController
Forgot issue | Forget password - Send email connection error | 39 | https://github.com/nekon0/SoWePray/issues/39 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Function | ForgotPasswordController
Admin screen issue | Most of the tabs in the sidebar of the map screen are broken | 40 | https://github.com/nekon0/SoWePray/issues/40 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Interface | GGmap screen
User level issue | Nothing different after user send a ticket to admin | 42 | https://github.com/nekon0/SoWePray/issues/42 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Function | TicketController
Novel issue | Edit novel lead to 500 error | 42 | https://github.com/nekon0/SoWePray/issues/46 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Function | EditNovelController, Update Novel Screen
Action issue | Novel's add to favor and report button not working | 46 | https://github.com/nekon0/SoWePray/issues/44 | Closed | AnhKTM | 2022-11-12 | 2022-11-13 | iter5 | Interface | Novel Detail Screen